SPM LAB REPORT TASK

1. Consider the Student Profile Management project

| S.N | Activity | Duration(days) | Strat Date | Finish Date | Predecessor | Resources & Involvement, % |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Planning & Analysis | 7 | 2024/2/20 | … |  | Team Leader (100%) |
| 2 | Requirement collection & definition | 15 | … | … | 1 | System Analyst (20%) |
| 3 | Designing | 7 |  |  | 2 | Designer (15%) |
| 4 | Development | 21 |  |  | 2,3 | Programmer (70%) |
| 5 | Testing | 8 |  |  | 2,3,4 | Test Engineer (20%) |
| 6 | Deployment | 7 |  |  | 3,4,5 |  |

Use Microsoft Project/OpenProj/Project Libre

(Please list steps and Screenshot of your task in Your Lab Report)

- Create Project name Student Profile Management

- Create work break down structure (WBC) with Activity_Name,	Duration(days),	Strat Date	Finish Date, Predecessor, Resources as listed in above table structure.

- Create a Project Scheduling basic and relationship based Gantt Diagram

- Show Work Break Down Structure (WBS) And Resource Breakdown Structure(RBS) diagram.

- List Task and Resource Uses report.

- Create Network modeling Diagram (PERT Chart and CPM ).

## 2. Create PERT diagram and Show Critical Path from following:

A project consists of the following activities:

| Activity | Predecessor | Duration |
| --- | --- | --- |
| A | — | 2 |
| B | A | 4 |
| C | A | 5 |
| D | B | 6 |
| E | C | 3 |
| F | D, E | 4 |

3. The following project activities are given:

| Activity | Duration (Days) |
| --- | --- |
| (1,2) | 4 |
| (1,3) | 6 |
| (2,4) | 5 |
| (3,4) | 3 |
| (4,5) | 2 |
| (3,5) | 8 |

Calculate:

- Draw PERT diagram and show Critical Path, Project Duration.

END