TRIBHUVAN UNIVERSITY

Institute of Science and Technology

SOFTWARE PROJECT MANAGEMENT

LABORATORY REPORT

Bachelor of Science in Computer Science and Information Technology (BSc. CSIT)

Seventh Semester

Topic: Project Scheduling, WBS/RBS, Gantt Chart and

PERT/CPM Network Diagram using ProjectLibre

Submitted by:

Name: _____________________________

Roll No / Symbol No: ______________

Program: BSc. CSIT, 7th Semester

Submitted to:

Department of Computer Science and Information Technology

# Objective

The objective of this lab is to understand the fundamentals of project scheduling and network modeling used in software project management. Specifically, this lab covers:

- Creating a project schedule using project management software (MS Project / OpenProj / ProjectLibre).

- Constructing a Work Breakdown Structure (WBS) and Resource Breakdown Structure (RBS).

- Generating basic and relationship-based Gantt charts.

- Producing Task Usage and Resource Usage reports.

- Drawing PERT (Program Evaluation and Review Technique) and CPM (Critical Path Method) network diagrams and identifying the critical path.

# Task 1: Student Profile Management System — Project Scheduling

Software used: ProjectLibre (open-source alternative to Microsoft Project). The same steps apply to MS Project / OpenProj with minor UI differences.

## (a) Creating the Project

Steps:

- Open ProjectLibre and select File → New.

- In the New Project dialog, enter the following details:

  - Project Name: Student Profile Management

  - Start Date: 20/02/2024

  - Manager: (Student Name)

  - Organization: (College Name)

- Click OK to create a blank project shell.

- Set the project calendar to 'Standard' from Project → Project Information, and confirm the working days/hours (8 hrs/day).

[Insert Screenshot: New Project dialog box showing Project Name = 'Student Profile Management']

## (b) Creating the Work Breakdown Structure (WBS)

Steps:

- Switch to the Gantt Chart view (View → Task Gantt).

- Enter each activity name in the Task Name column, in outline order 1 to 6.

- Enter the Duration for every task in days.

- Enter the Start Date for Task 1 (20/02/2024); ProjectLibre auto-computes subsequent dates once predecessors are linked.

- In the Predecessors column, enter the task numbers as given (e.g. Task 4 → '2,3').

- Double-click each task → Resources tab → assign the resource and the % Units of involvement (e.g. Designer at 15%).

[Insert Screenshot: Task sheet / Gantt table filled with all 6 activities, durations, dates, predecessors and resources]

### WBS Data Table (as entered in ProjectLibre)

| S.N | Activity | Duration (days) | Start Date | Finish Date | Predecessor | Resource (% Involvement) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Planning & Analysis | 7 | 2024-02-20 | 2024-02-26 | — | Team Leader (100%) |
| 2 | Requirement Collection & Definition | 15 | 2024-02-27 | 2024-03-12 | 1 | System Analyst (20%) |
| 3 | Designing | 7 | 2024-03-13 | 2024-03-19 | 2 | Designer (15%) |
| 4 | Development | 21 | 2024-03-20 | 2024-04-09 | 2, 3 | Programmer (70%) |
| 5 | Testing | 8 | 2024-04-10 | 2024-04-17 | 2, 3, 4 | Test Engineer (20%) |
| 6 | Deployment | 7 | 2024-04-18 | 2024-04-24 | 3, 4, 5 | — |

Note: Dates are computed on a Finish-to-Start (FS) dependency basis — a successor task begins the day after the latest finishing predecessor. Total project duration = 65 calendar days (20 Feb 2024 – 24 Apr 2024).

## (c) Project Scheduling – Gantt Diagrams

Steps to generate the Gantt chart:

- With all tasks, durations and dependencies entered, ProjectLibre automatically draws bars in the Gantt Chart pane on the right.

- For the Basic Gantt Chart, view only task bars against the timeline (View → Gantt Chart).

- For the Relationship-based Gantt Chart, ensure predecessor links are entered so that dependency arrows (Finish-to-Start) are drawn connecting related task bars.

- Right-click the Gantt area → Bar Styles to customize colors (optional).

### (i) Basic Gantt Chart

Fig 1: Basic Gantt Chart – Student Profile Management System

### (ii) Relationship-based Gantt Chart (with dependency arrows)

Fig 2: Relationship-based Gantt Chart showing Finish-to-Start dependency arrows

## (d) Work Breakdown Structure (WBS) and Resource Breakdown Structure (RBS) Diagrams

Steps:

- In ProjectLibre, go to View → WBS Chart (or, if unavailable in the installed version, construct the WBS chart manually using the outline numbers assigned to each task, as shown below).

- The WBS decomposes the project into phases (Level 1) and further into deliverable-based work packages (Level 2).

- For the RBS, go to View → Resource Sheet to list all resources, then group them by category (Human Resources / Material Resources) to draw the RBS hierarchy.

### Work Breakdown Structure (WBS)

Fig 3a: WBS – Phases 1 to 3

Fig 3b: WBS – Phases 4 to 6

### Resource Breakdown Structure (RBS)

Fig 4: Resource Breakdown Structure (RBS) – Student Profile Management System

## (e) Task Usage and Resource Usage Reports

Steps:

- Go to View → Task Usage to see each task with its assigned resource(s) and the time-phased work (hours).

- Go to View → Resource Usage to see each resource with the list of tasks it is assigned to and total work.

- Work is computed as: Work = Duration × Resource Units (e.g., Programmer at 70% for 21 days × 8 hrs/day = 117.6 hrs).

### Task Usage Report

| S.N | Task | Duration | Resource | Units | Work (hrs) |
| --- | --- | --- | --- | --- | --- |
| 1 | Planning & Analysis | 7d | Team Leader | 100% | 56.0 |
| 2 | Requirement Collection & Definition | 15d | System Analyst | 20% | 24.0 |
| 3 | Designing | 7d | Designer | 15% | 8.4 |
| 4 | Development | 21d | Programmer | 70% | 117.6 |
| 5 | Testing | 8d | Test Engineer | 20% | 12.8 |
| 6 | Deployment | 7d | Not assigned | — | 0.0 |

### Resource Usage Report

| S.N | Resource | Assigned Task(s) | Units | Total Work (hrs) |
| --- | --- | --- | --- | --- |
| 1 | Team Leader | Planning & Analysis | 100% | 56.0 |
| 2 | System Analyst | Requirement Collection & Definition | 20% | 24.0 |
| 3 | Designer | Designing | 15% | 8.4 |
| 4 | Programmer | Development | 70% | 117.6 |
| 5 | Test Engineer | Testing | 20% | 12.8 |

[Insert Screenshot: ProjectLibre Task Usage view and Resource Usage view]

## (f) Network Modeling Diagram — PERT Chart and CPM

Steps:

- Go to View → Network Diagram (PERT Chart) in ProjectLibre to view the Activity-on-Node (AON) network automatically generated from the task list and predecessors.

- Each node box shows the task ID, name, duration, and (once the CPM calculation is run via Tools → Options or the built-in scheduler) the Early Start (ES), Early Finish (EF), Late Start (LS) and Late Finish (LF).

- Critical tasks (zero slack/float) are usually highlighted in red by the tool.

- The Critical Path is the longest path through the network and determines the minimum project duration.

Fig 5: PERT/CPM Network Diagram (AON) — Student Profile Management System

Analysis: Since every activity in this project depends directly on the completion of all its predecessors in a single sequential chain (1→2→3→4→5→6), there is only one path through the network. Hence all six activities are critical, with zero slack, and the Critical Path is:

Critical Path: 1 → 2 → 3 → 4 → 5 → 6

Project Duration = 7 + 15 + 7 + 21 + 8 + 7 = 65 days

# Task 2: PERT Diagram and Critical Path

Given the following project activities:

| Activity | Predecessor | Duration |
| --- | --- | --- |
| A | — | 2 |
| B | A | 4 |
| C | A | 5 |
| D | B | 6 |
| E | C | 3 |
| F | D, E | 4 |

## Forward Pass (Earliest Start / Earliest Finish)

- ES(A) = 0, EF(A) = 0 + 2 = 2

- ES(B) = EF(A) = 2, EF(B) = 2 + 4 = 6

- ES(C) = EF(A) = 2, EF(C) = 2 + 5 = 7

- ES(D) = EF(B) = 6, EF(D) = 6 + 6 = 12

- ES(E) = EF(C) = 7, EF(E) = 7 + 3 = 10

- ES(F) = max(EF(D), EF(E)) = max(12, 10) = 12, EF(F) = 12 + 4 = 16

## Backward Pass (Latest Start / Latest Finish)

- LF(F) = 16, LS(F) = 16 − 4 = 12

- LF(D) = LS(F) = 12, LS(D) = 12 − 6 = 6

- LF(E) = LS(F) = 12, LS(E) = 12 − 3 = 9

- LF(B) = LS(D) = 6, LS(B) = 6 − 4 = 2

- LF(C) = LS(E) = 9, LS(C) = 9 − 5 = 4

- LF(A) = min(LS(B), LS(C)) = min(2, 4) = 2, LS(A) = 2 − 2 = 0

## Slack / Float Table

| Activity | ES | EF | LS | LF | Slack (LS−ES) | Critical? |
| --- | --- | --- | --- | --- | --- | --- |
| A | 0 | 2 | 0 | 2 | 0 | Yes |
| B | 2 | 6 | 2 | 6 | 0 | Yes |
| C | 2 | 7 | 4 | 9 | 2 | No |
| D | 6 | 12 | 6 | 12 | 0 | Yes |
| E | 7 | 10 | 9 | 12 | 2 | No |
| F | 12 | 16 | 12 | 16 | 0 | Yes |

## PERT / CPM Network Diagram

Fig 6: PERT Network Diagram – Activities A to F

Path comparison:

- Path A–B–D–F = 2 + 4 + 6 + 4 = 16 days

- Path A–C–E–F = 2 + 5 + 3 + 4 = 14 days

Critical Path: A → B → D → F

Project Duration = 16 days

# Task 3: AOA Network Diagram and Critical Path Calculation

Given activities represented in (i, j) node notation:

| Activity (i, j) | Duration (Days) |
| --- | --- |
| (1, 2) | 4 |
| (1, 3) | 6 |
| (2, 4) | 5 |
| (3, 4) | 3 |
| (4, 5) | 2 |
| (3, 5) | 8 |

## Forward Pass — Earliest Event Time E(j)

- E(1) = 0

- E(2) = E(1) + 4 = 0 + 4 = 4

- E(3) = E(1) + 6 = 0 + 6 = 6

- E(4) = max[E(2)+5, E(3)+3] = max[4+5, 6+3] = max[9, 9] = 9

- E(5) = max[E(4)+2, E(3)+8] = max[9+2, 6+8] = max[11, 14] = 14

## Backward Pass — Latest Event Time L(i)

- L(5) = 14

- L(4) = L(5) − 2 = 14 − 2 = 12

- L(3) = min[L(4)−3, L(5)−8] = min[12−3, 14−8] = min[9, 6] = 6

- L(2) = L(4) − 5 = 12 − 5 = 7

- L(1) = min[L(2)−4, L(3)−6] = min[7−4, 6−6] = min[3, 0] = 0

## Event Time Table

| Event (Node) | Earliest Time E | Latest Time L | Slack (L−E) | Critical? |
| --- | --- | --- | --- | --- |
| 1 | 0 | 0 | 0 | Yes |
| 2 | 4 | 7 | 3 | No |
| 3 | 6 | 6 | 0 | Yes |
| 4 | 9 | 12 | 3 | No |
| 5 | 14 | 14 | 0 | Yes |

## AOA (Activity-on-Arrow) Network Diagram

Fig 7: AOA Network Diagram — Nodes 1 to 5

An activity (i, j) lies on the critical path only if E(i)=L(i), E(j)=L(j), and E(i)+duration=E(j). Applying this test:

- (1,3): E(1)+6 = 0+6 = 6 = E(3) ✓ and both nodes critical → Critical

- (3,5): E(3)+8 = 6+8 = 14 = E(5) ✓ and both nodes critical → Critical

- (1,2), (2,4), (3,4), (4,5): fail the equality test → Not critical

Critical Path: 1 → 3 → 5   (via activities (1,3) and (3,5))

Project Duration = 6 + 8 = 14 days

# Conclusion

This lab provided hands-on experience in software project scheduling using a project management tool (ProjectLibre) and manual network analysis. Key learnings include:

- Creating a project plan with a Work Breakdown Structure (WBS) linking tasks, durations, dates, dependencies and resources.

- Visualizing the schedule through basic and relationship (dependency-linked) Gantt charts.

- Decomposing the project into WBS and RBS hierarchies for clearer planning and resource allocation.

- Generating Task Usage and Resource Usage reports to track effort distribution.

- Applying the forward pass and backward pass technique of PERT/CPM to compute ES, EF, LS, LF, slack, and to identify the critical path — the sequence of activities with zero slack that determines the minimum project completion time.

For the three exercises: the Student Profile Management project has a critical path of 65 days along all six sequential activities; the six-activity PERT problem has a critical path A-B-D-F of 16 days; and the five-node AOA network has a critical path 1-3-5 of 14 days.